## Sheet1
ISSUE | RESOLUTION STATUS | ADDRESSED BY | PRIORITY
Dynamic Profile fields | Resolved | Tejas | High
Uniqueness on email constraint | Open |  | High
Redundant fields in Edit Profile | Resolved | Tejas | High
Formatting on profile page | Resolved - Partial | Tejas | Low
Places API integration | Open |  | High
Profile Updates | Resolved | Tejas | High
Nearby List | Open |  | High
Checkbox removal near contact | Open |  | Low
Email Login | Open |  | Medium
Avatars | Resolved | Tejas | High
Change password | Open |  | High
Delete account | Resolved | Tejas | High
Edit Profile Spinner GUI formatting | Open |  | Medium
Contacts avatar support | Open |  | High
Password encryption | Resolved | Tejas | High
Firebase integration | Open |  | High